DIRA  |  SAS

Technology Solutions for Growing Institutions  |  Bamenda, North West Region, Cameroon

CONCEPT NOTE -- FOR OFFICIAL AND INSTITUTIONAL USE

CONCEPT NOTE

Northwest Government and Public Institutions

Digital Readiness Survey (NW-GPIDRS)

Submitted to: Regional Delegation of MINPOSTEL, North West Region  |  July 2026

| Field | Details |
| --- | --- |
| Programme Name | Northwest Government and Public Institutions Digital Readiness Survey (NW-GPIDRS) |
| Implementing Party | DIRA SAS, Bamenda (RC.BDA.2026.B.000339). All implementation costs borne by DIRA. |
| Institutional Partner | Regional Delegation of MINPOSTEL, North West Region |
| Co-Partner (Active) | Regional Delegation of MINPMEESA, NW Region |
| Geographic Scope | North West Region, Cameroon (all eight Divisions) |
| Target Institutions | 20 to 35 regional delegations, divisional offices, sub-divisional offices, local councils, and Governor's Office |
| Duration | 6 to 8 months from MOU signing |
| Indicative Programme Value | 30,000,000 to 50,000,000 XAF (borne entirely by DIRA SAS) |
| Policy Alignment | SND30 (2020-2030), PATNUC (P173240 / IDA 69870-CM), MINPOSTEL strategic mandate, Law No. 2010/012 on Cybersecurity |

1.  Context and Problem Statement

The North West Region of Cameroon has a functioning layer of public administration: eight divisional offices, dozens of sub-divisional offices, regional ministerial delegations for most national ministries, local council chambers, and the Governor's Office. Collectively these institutions serve hundreds of thousands of citizens. They generate, process, and store the data that regional governance runs on association registries, cooperative records, land files, civil registration documents, tax data, public health records.

A DIRA field visit to the office of the Senior Divisional Officer for Mezam Division in July 2026 produced a concrete finding: the office had no database of registered associations operating in its territory. Registries were in paper ledgers. There was nothing searchable, nothing backed up, nothing shareable with a sister office. Association registration is one of the SDO's core statutory functions.

This gap is not peculiar to Mezam. MINPOSTEL's own Secretary General stated in February 2026 that digital tools across Cameroonian public administrations often develop without common frameworks or shared guidance, creating interoperability failures and unresolved data governance questions. The World Bank's PATNUC assessments echo the same finding: several government agencies remain undigitised and platforms are not integrated across institutions.

The practical consequence is that MINPOSTEL currently has no institution-level data on the digital state of government offices in the North West Region. It cannot aim PATNUC resources at the specific gaps that exist here, because no one has mapped them. DIRA proposes to do that mapping.

Benchmark: MINPOSTEL's open tender N°024/AONO/MPT/CIPM/2026 valued a comparable field research and diagnostic study at 95,000,000 XAF for a three-month national engagement. DIRA is offering a regionally equivalent programme at zero cost to MINPOSTEL.

2.  Programme Objectives

•  Assess the digital infrastructure, data management practices, and technology capacity of 20 to 35 public institutions across the North West Region within 6 to 8 months.

•  Deliver a written Digital Readiness Report to each assessed institution within 7 business days of the visit.

•  Compile findings into the Northwest Government Digital Readiness Index the first institution-level public sector digital baseline for the region.

•  Produce a combined Northwest Regional Digital Ecosystem Report integrating government findings with the ongoing NWDRS private sector data.

•  Give MINPOSTEL field-validated, regionally specific data for PATNUC targeting, SND30 reporting, and future public sector digitisation interventions.

•  Build a replicable methodology that can be extended to other regions.

3.  Target Institutions and Scope

The programme covers four categories of public institution within the North West Region, all falling within MINPOSTEL's mandate for public sector digital transformation under PATNUC and SND30:

| # | Institution Category | Target Count | Geographic Focus |
| --- | --- | --- | --- |
| 1 | Regional Ministerial Delegations | 8 to 12 | MINPMEESA, MINJEC, MINAGRI, MINSANTE, MINAS, MINEDUB, MINFOPRA, MINTSS -- Bamenda-based |
| 2 | Divisional and Sub-Divisional Offices | 6 to 10 | SDO offices for all eight Divisions: Mezam, Momo, Boyo, Bui, Donga-Mantung, Menchum, Ngo-Ketunjia, Lebialem |
| 3 | Local Councils | 4 to 8 | Selected councils in Bamenda, Bali, Wum, Kumbo, Nkambe -- prioritised by population served |
| 4 | Governor's Office / Regional Secretariat | 1 to 2 | Subject to authorisation -- MINPOSTEL's backing makes this access feasible |

The NW-GPIDRS runs in parallel with the Northwest Digital Readiness Survey (NWDRS) that DIRA is implementing with MINPMEESA for private sector institutions. The two programmes will be integrated into a single Northwest Regional Digital Ecosystem Report at completion, covering both public and private sectors; a regional intelligence product available to both ministries.

4.  Assessment Methodology

Each institution receives a structured half-day on-site assessment. The methodology is consistent with the professional research standards reflected in MINPOSTEL's own commissioned studies, including the diagnostic and benchmarking approach used in tender N°024/AONO/MPT/CIPM/2026. Six domains are assessed:

| # | Domain | What It Measures |
| --- | --- | --- |
| 1 | Connectivity and Hardware | Computers per staff, internet type and reliability, power, networking, device condition |
| 2 | Data and Records Management | How official registries and citizen files are stored, backed up, and retrieved; paper-to-digital ratio |
| 3 | Digital Public Services | Online service delivery, e-government readiness, citizen-facing digital access points |
| 4 | Inter-Institutional Communication | Data sharing with other offices, use of official email, integration with national platforms (SIGIPES, ANTILOPE, etc.) |
| 5 | Staff Digital Capacity | Computer literacy rates, prior formal training, presence of an IT or systems officer |
| 6 | Governance and Procurement Readiness | IT budget line, prior technology projects, approval authority for digital procurement |

Each domain is scored 1 to 5. Scores feed an institution-level profile and a domain-level regional average, forming the statistical backbone of the Northwest Government Digital Readiness Index.

5.  Programme Deliverables

| Deliverable | Recipient | Timeline |
| --- | --- | --- |
| Digital Readiness Report for each assessed institution | Each institution | Within 7 business days of visit |
| Quarterly progress briefings (Months 2, 4, 6) | MINPOSTEL NW Delegation | End of each quarter |
| Northwest Government Digital Readiness Index | MINPOSTEL NW + national (on request) | Month 7 to 8 |
| Northwest Regional Digital Ecosystem Report (public + private sectors combined) | MINPOSTEL + MINPMEESA | Month 8 |
| Final programme report with policy recommendations | MINPOSTEL NW Delegation | Month 8 |
| PATNUC-formatted regional data package (optional) | MINPOSTEL national, on request | On request |

6.  Programme Timeline

| Period | Phase | Activities |
| --- | --- | --- |
| Month 1 | Launch | MOU signing, Letter of Authorisation issued, target institution outreach, first assessments |
| Months 2-3 | Wave 1 | 8 to 12 institutions assessed, individual reports delivered, Progress Briefing 1 |
| Months 4-5 | Wave 2 | 8 to 12 institutions assessed, individual reports delivered, mid-point review, Progress Briefing 2 |
| Month 6 | Wave 3 | Final institutions assessed, all reports delivered, data aggregation begins, Progress Briefing 3 |
| Month 7 | Analysis | Cross-institution analysis, domain benchmarking, Government Digital Readiness Index compiled |
| Month 8 | Reporting | Regional Digital Ecosystem Report finalised, final programme report delivered, closing presentation to MINPOSTEL |

7.  Financial Model

DIRA bears the full cost of programme implementation. There is no financial obligation, budget line, or cost of any kind on the part of MINPOSTEL or the Government of Cameroon.

| Cost Category | Estimated Budget (XAF) | Borne By |
| --- | --- | --- |
| Field assessments and assessor time | 8,000,000 to 12,000,000 | DIRA |
| Transport and logistics across all 8 Divisions | 4,000,000 to 7,000,000 | DIRA |
| Individual report production (20 to 35 reports) | 3,000,000 to 5,000,000 | DIRA |
| Data analysis and Index compilation | 5,000,000 to 8,000,000 | DIRA |
| Final reports, printing, and delivery | 2,000,000 to 4,000,000 | DIRA |
| Programme coordination (8 months) | 8,000,000 to 14,000,000 | DIRA |
| TOTAL INDICATIVE PROGRAMME VALUE | 30,000,000 to 50,000,000 XAF | 100% DIRA Digital Era |

MINPOSTEL contributes institutional partnership and the Letter of Authorisation. In return it receives the full data output and joint credit for a programme it paid nothing to run.

8.  PATNUC Alignment

PATNUC is structured around four components. The first covers digital strategy, public policy, and regulation for digital transformation. The fourth covers project management and citizen engagement. Both are fed directly by field data on the actual digital state of public institutions. PATNUC's steering committee, meeting in December 2025, called 2026 the programme's decisive year, committed a budget of 28.3 billion XAF for the year's activities, and stated explicitly that the programme must be visible on the ground across regions. A government digital readiness baseline for the North West Region -- the only Anglophone region of Cameroon, which has historically received less programme attention -- is a concrete, documentable regional contribution to those objectives.

PATNUC also issued a call for a digital transformation training consultant for public agents in March 2026, specifically to build civil servant capacity via e-learning (reference: N°002/ASMI/MINPOSTEL/PATNUC/UGP/RC2/SPM/SJPM/2026). The NW-GPIDRS generates the institution-level capacity data that makes such training programmes targetable. Without knowing which offices have computers, which staff have prior IT training, and which institutions have no IT officer at all, a national training roll-out cannot be efficiently prioritised.

9.  Why DIRA

DIRA has been operating in Bamenda since its founding. The team has built digital infrastructure for institutions in the North West Region, navigated the region's operational realities, and established working relationships with key public and private sector actors. This is not transferred expertise from another city. It is local knowledge from daily operation.

DIRA is currently implementing the Northwest Digital Readiness Survey with MINPMEESA -- assessments of private sector SMEs and cooperative credit unions across the region began in July 2026. The NW-GPIDRS for public institutions runs on the same methodology. A single DIRA team, with active ministry partnerships on both sides, can deliver a combined public-private digital readiness picture for the North West Region that no other organisation in Cameroon is positioned to produce.

10.  Policy Alignment Summary

| Framework | How NW-GPIDRS Contributes |
| --- | --- |
| SND30 (2020-2030) | Produces the first institution-level regional baseline for public sector digital readiness; directly feeds SND30 measurement and reporting for the digital economy priority sector |
| PATNUC Component 1 (digital strategy and policy) | Generates the field evidence that Component 1's policy and regulatory frameworks need to be regionally grounded; feeds PATNUC's regional implementation planning |
| PATNUC Component 4 (citizen engagement) | A field programme with active public institution involvement and a public-facing output (Digital Readiness Reports) is exactly the kind of citizen-level engagement Component 4 mandates |
| PATNUC 2026 field presence mandate | The steering committee explicitly called for strong regional field presence in 2026. The NW-GPIDRS provides it in the North West Region at no cost to PATNUC. |
| Law No. 2010/012 on Cybersecurity | The assessment covers data security practices, backup procedures, and access controls -- each institution's obligations under Cameroonian cybersecurity law |
| NWDRS (MINPMEESA, active) | The two programmes combine into the Northwest Regional Digital Ecosystem Report -- a cross-sector baseline no single ministry programme could produce independently |

11.  Requested Actions

1.  Review and sign the attached Memorandum of Understanding

2.  Issue a Letter of Authorisation on MINPOSTEL delegation letterhead  --  a draft template is enclosed

3.  Where possible, facilitate introductions to the Governor's Office and divisional administration offices requiring senior-level access authorisation

4.  Agree on a programme launch date

To proceed with signing or schedule a programme presentation: diracmr.com ¦ info@diracmr.com ¦ Bamenda, North West Region, Cameroon

DIRA SAS  |  NW-GPIDRS Concept Note v1.1  |  July 2026  |  CONFIDENTIAL